## Release 1
Screen Name | Environment | Issue Description | Priority | Dev Status | NOTE | QA Status
Home | Chorme/Microsoftedge/Firfox | Careers link not working when click on careers (Know issue) | High | fixed | Release 1 careers page/links will be hidden
| Chorme/Microsoftedge/Firfox | Case studies link background color is displaying but mockup it is not showing - Reimagine&Redefine popup | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Case studies link should have underlined - Reimagine&Redefine popup | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Reimagine&Redefine popup size should display as high - it should be decreased | Low | fixed |  | on hold
| Chorme/Microsoftedge/Firfox | Reimagine&Redefine popup background image is not displayed completely as per design | Medium | fixed | Design team approved | Design team approved
| Chorme/Microsoftedge/Firfox | If we click to learn more Reimagine&Redefine popup - Page slightly going up and content is not displaying properly | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | After value text there will be dots(…) showing in Reimagine&Redefine popup | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Reimagine&Redefine popup - Backgroung image is not displaying completely | Medium | fixed | Design team approved | Design team approved
| Chorme/Microsoftedge/Firfox | Taking time to load the images - Slow loading (Know issue) | High | fixed | images are updated | Working Fine
| Chorme/Microsoftedge/Firfox | Instead of "MAKE A DIFFERENCE" text "THAT MAKE A DIFFERENCE" text is displaying | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | AI-Enabled Products, Solutions & Services - Font size is displaying high as compared with mocup | Low | fixed | Design team approved | Design team approved
| IE | In IE all the screen we have issues with images - Images are not displaying properly and misalignments in icons and content not displaying for few popups | High | on hold | IE has lesser priority and will be worked upon later.it should work on IE => 12 | on hold
| Chorme/Microsoftedge/Firfox | We develop solutions that enable you to realize the true potential of AI text - Products text is missing like text should be products and solutions | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Advanced Analytics, Engineering & Visualization practices - Instead of engineering it should be "Data Engineering" - Data text missing | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | End-to-end Solutions, 24/7 Support, Technology Agnostic, Smart Innovations icons image size should be decreased and for background image are not displaying completely | Low | fixed | Design team approved | Design team approved
| Chorme/Microsoftedge/Firfox | Industries heading and all industry names and read more link missing in home screen | High | release 3 | for release 1 we are not showing, for next release we will. | Release 2
| Chorme/Microsoftedge/Firfox | Industries images and icon image size should be decreased - displaying high compare to mocups | Low | fixed | Design team updated/approved new design | Design team approved
| Chorme/Microsoftedge/Firfox | Our services section - AI/ML services should be displaying instead of AI/ML | Medium | fixed |  | Still In progress
| Chorme/Microsoftedge/Firfox | Learn More Link in Our services section - Arrow missing for Learn More and For all Leran More links should be different colors as per mocups | Low | release 2 | for release 2. In release 1 we will keep same color - Design team approved | Release 2
| Chorme/Microsoftedge/Firfox | Company names not in line as per design in home screen | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | As per design "Improved campaign effectiveness" text missing in Propensity modelling popup under case studies | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Learn More Link in Case studies section - For all Leran More links should be different in colors as per mocups | Low | release 2 | for release 2. In release 1 we will keep same color - Design team approved | Release 2
| Chorme/Microsoftedge/Firfox | For the last popup Instead of "RECOMMENDATION SYSTEM" should be display "PREVENTIVE MAINTENANCE" under case studies also description also be change as per design | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Careers link not working when click on careers control - Lets grow together section | High | release 2 | for release 2. currently hiding the links for careers | Release 2
| Chorme/Microsoftedge/Firfox | Social links not working when we click on social icons | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Careers link not working under References section in footer | High | release 2 | for release 2. links will be hidden | Release 2
| Chorme/Microsoftedge/Firfox | Risk analysis icon is mismatch with inner screen when click on Learn More |  | fixed
| Chorme/Microsoftedge/Firfox | PREVENTIVE MAINTENANCE description should be changed as per design |  | fixed
| chrome/Mozilla | In Our services section if we can add arrows it good to know other slides (Suggestion) | Low | fixed
| chrome/Mozilla | Under Carriers in "Learn more" is not redirecting to down page. | Low | fixed
| chrome/Mozilla | Careers: under Working with us content need to add full stop in the last after carrers@amnetdigital.com | Low | fixed
| chrome/Mozilla | Careers : Missing exclamation mark for the head message in webpage compared to design page. | Low | fixed
| chrome/Mozilla | Home Page: Under Out Services in Cloud when we click on Learn more it's not redirecting to Cloud Page | Medium | fixed
| chrome/Mozilla | Careers: Under Current openings need to add link for "Careers@amnetdigital.com" | Medium | fixed
About Us | Chorme/Microsoftedge/Firfox | Innovation Catalyst text is displaying instead of "Your Innovation Catalyst" | Medium | fixed | design team approved
| Chorme/Microsoftedge/Firfox | Case studies link background color is displaying but mockup it is not showing - Your Innovation Catalyst popup | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Case studies link should have underlined - Your Innovation Catalyst popup | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Your Innovation Catalyst popup size should display as high - it should be decreased | Low | fixed | design team approved | design team approved
| Chorme/Microsoftedge/Firfox | Your Innovation Catalyst popup background image is not displayed completely as per design | Medium | fixed | design team approved | design team approved
| Chorme/Microsoftedge/Firfox | Vision Text should right aligned as per design | Low | release 2 | design team approved | design team approved
| Chorme/Microsoftedge/Firfox | All the content size in about us screen should high compare to designs | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | View Location link is not working in our locations section | High | release 2 | links will be hidden for release 1 | release 2
| Chorme/Microsoftedge/Firfox | View location Link in our Location section - For all View location links should be different in colors as per mocups | Low | release 2 | links will be hidden for release 1 | release 2
| Chorme/Microsoftedge/Firfox | Careers link not working when click on careers control - Lets grow together section | High | release 2 | fixed | release 2
Contact Us | Chorme/Microsoftedge/Firfox | Contact Us image is taking time to load | High | fixed | image updated
| Chorme/Microsoftedge/Firfox | First Name and Last Name text should not displaying as per design - In desin Name text with fields and the below text fields First and Last is displaying | Medium | fixed
| Chorme/Microsoftedge/Firfox | First Name ,Last Name and Enter email within the text boxes should be removed | Low | fixed
| Chorme/Microsoftedge/Firfox | Email Address heading should be displyed as Email | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | "sri@com" without . Symbol accepting email address - should display validation message | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Success message should be display after submitting the details in contact us page | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | View Location link is not working in our locations screen | High | release 2 | links will be hidden for release 1 | release 2
| Chorme/Microsoftedge/Firfox | View location Link in our Location section - For all View location links should be different in colors as per mocups | Low | release 2 | links will be hidden for release 1 | release 2
| Chorme/Microsoftedge/Firfox | First name and last Name accepting the numbers | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Without Message given in your message section we are submitting the form ( success popup is displaying ) | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Field wise error validations is not displaying | High
| Chorme/Microsoftedge/Firfox | When we enter invalid data into fields and click on ok control total page is refreshed | High
| Chorme/Microsoftedge/Firfox | For job sections, each section will close on another section selection | Medium
Case Studies | Chorme/Microsoftedge/Firfox | Taking time to load the images (Know issue) | Medium | fixed | images are updated
| Chorme/Microsoftedge/Firfox | Header line font size need to be resize | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Contact Us Backgroud clolor should be visibe to identify a button. | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Typo error on customers'(expected should be customer's) under Requirement. | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Duplication of subject in both "PROPENSITY MODELLING & RECOMMENDATION SYSTEM" and "CUSTOMER PROFILE" | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Duplication of Header & Subject "PROPENSITY MODELLING & RECOMMENDATION SYSTEM" | High | fixed |  | Working Fine
Services | Chorme/Microsoftedge/Firfox | Seeing mismatch from mockup design headline to webpage headline. | Low | fixed
| Chorme/Microsoftedge/Firfox | Font & Background not as per design provided | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Contact Us Backgroud clolor not as per design | Medium | fixed |  | Working Fine
Careers | Chorme/Microsoftedge/Firfox | Maintain system documentation and user guides - Content Displaying multiple times | Low | in progress
|  | Instead of "Application Engineer - MEAN stack Developer - JD" text "Application Engineer" displaying | Low | in progress
| Andriod /IOS | Loading images taking time for all the devices | High | fixed
| Andriod /IOS | If we clear histroy and cookies then again loading taking long time reload the screen | High
| IOS | Iphone11 :Page content is displaying but images not loading also content not aligned properly | High
| Safari 13.0.5 (Apple laptop) | Safari browser amnet page not loading | High
|  | Our service section scrolling sliders ovrerlapping when we scroll up and down in home screen | High | fixed |  | Working Fine

## Release 2
Screen Name | Environment | Issue Description | Priority | Dev Status | NOTE | QA Status
Home | Chorme/Microsoftedge/Firfox | Missing text "AI-Enabled tools will generate $2.9 trillion in business value by 2021" ~ U D A C I T Y | high | Removed as per requirement |  | NA
| Chorme/Microsoftedge/Firfox | Our service section : for AI / ML SERVICES - classname is displaying instead of class | low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | If we are reading content in the bottom of the page in any screen, then When user click on the Amnet digital logo in the page header, it should be automatically scrolled up to the header section. | low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Page not located to exact place,When we click on learnmore link "Reimagine & Redefine" popup | low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Arrow missing for learn more link in our services section | low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Company names logos section is missing in home screen | high | Removed as per requirement |  | NA
| Chorme/Microsoftedge/Firfox | Case Studies section in home page - Missing Learn more links for each popup | high | fixed |  | Working Fine
|  | Dobule 'In' is displaying under CONSULTING content - services screen | medium | fixed |  | Working Fine
About Us | Chorme/Microsoftedge/Firfox | Page not located to exact place,When we click on learnmore link "Innovation Catalyst" popup | low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Vision and mission sections are not as per design provided | medium | in-progress |  | Working Fine
Services | Chorme/Microsoftedge/Firfox | For all sections content alignment missing | low | in-progress |  | Working Fine
Case stidies | Chorme/Microsoftedge/Firfox | VIRTUAL SHOPPING ASSISTANT section : '/ 'missing for CVCNN | low | fixed |  | Working Fine
|  | If we are reading content in the bottom of the page in any screen and click on any link in header, it should be automatically scrolled up to the header section but displaying bottom of the screen only | Medium | fixed |  | Working Fine
| Safari 14.1 browser | PLATFORM ENGINEERING content is misaligned in our services section (11 inch apple laptop screen ) | low | fixed |  | Working Fine
|  | Case studies ,Learn more arrow mark is missing for case studies link | low | fixed |  | Working Fine
|  | Contact us image is misaligned with text | low |  |  | Working Fine
|  | About us page mission and vision sections images and content is misaligned | low | fixed |  | Working Fine
| Iphone mobile | Contact us not displaying in menu list | High | fixed |  | Working Fine
|  | When we tap on any menu link, the dropdown should disappear. It is still showing to access another link | Medium | fixed |  | Working Fine
|  | Case studies(popup)link for every screen it is misaligned | High | fixed |  | Working Fine

## Release 3
Screen Name | Environment | Issue Description | Priority | Dev Status | NOTE | QA Status
Sub Sevices | Chorme/Microsoftedge/Firfox | Data Annotation displaying instead of Data Labeling sub services scree | Medium | Design Updated |  | Working Fine
| Chorme/Microsoftedge/Firfox | AIML is displaying instead of AI / ML sub services screen | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | We'are available section not displaying in all sub services screens | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | View details control is not working for all the sub services screens (Not navigated to exact screen) | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | In design heading is displaying with cloud services but in website only cloud is displaying | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Missing ondemand availablity ,broad network availability,controlled& optimized costs in cloud sub services screen | Medium | Next Release
| Chorme/Microsoftedge/Firfox | Include Mobile testing in Quality assurence description - sub services screen | Medium | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Infrastructure,Application Engineering both located in different as per design | Low | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | Full background header image is not displaying - data-annotation | Medium | Next Release
| Chorme/Microsoftedge/Firfox | Advanced Analytics header text is not as per text provided | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | AI /ML and Advanced analytics - This screens few section text is not updated. | High | fixed |  | Working Fine
| Chorme/Microsoftedge/Firfox | AL/ML ,Data Annotation,User Experience Background images need to change | High | Next Release
| Chorme/Microsoftedge/Firfox | We are avaiable section soft services BG images need to change | High | Next Release
| Tablet | Header complete background images not displaying in tablet view | Medium | Next Release
| Chorme/Microsoftedge/Firfox | Section wise headings missing for AL/ML | Medium | Next Release
| Chorme/Microsoftedge/Firfox | Services page images taking more time to load (AI/ML, Data Engineering, Cloud, Data Annotation) | High | Next Release
IPhone | Iphone 6 s | Text is not aligned properly in iphone devices | Medium
| Ipod Pro | View details control is not aligned properly | Medium | fixed |  | Working Fine
| Apple Laptop - Safari | Full background header image is not displaying - all the screens in tablet and 11 inch laptop | Medium | Next Release
| Iphone | Page is not loading 8,9 version in safari - Iphone 6,6s,6plus | High | Next Release
New Changes
|  | User-experience, Data-engineering, Data-management text added. |  |  |  | Working Fine
|  | The View Details button is working. |  |  |  | Working Fine
|  | We’re available is displaying. |  |  |  | Working Fine
|  | Data-Engineering has been added. |  |  |  | Working Fine
|  | User-Experience has been added except Background Image. |  |  |  | Working Fine
|  | Advanced Analytics has been added with dummy text.(All images and icons are added) |  |  |  | Working Fine
|  | Data-Management has been added except “Document and Content Management Image and icon“. |  |  |  | Working Fine
|  | Removed network analysis from Advanced Analytics page. |  |  |  | Working Fine
|  | Removed dashboards from ai ml |  |  |  | Working Fine
|  | AI / ML has been added Except for the background image. |  |  |  | Working Fine
|  | Advanced analytics has been added |  |  |  | Working Fine