## Sheet1
Screen Name | Environment | Issue Description | Priority
Home Screen | Chorme | Careers link not working when click on careers (Know issue) | High
| Chorme | Case studies link background color is displaying but mockup it is not showing - Reimagine&Redefine popup | Low
| Chorme | Case studies link should have underlined - Reimagine&Redefine popup | Low
| Chorme | Reimagine&Redefine popup size should display as high - it should be decreased | Low
| Chorme | Reimagine&Redefine popup background image is not displayed completely as per design | Medium
| Chorme | If we click to learn more Reimagine&Redefine popup - Page slightly going up and content is not displaying properly | High
| Chorme | After value text there will be dots(…) showing in Reimagine&Redefine popup | Low
| Chorme | Reimagine&Redefine popup - Backgroung image is not displaying completely | Medium
| Chorme | Taking time to load the images - Slow loading (Know issue) | High
| Chorme | Instead of "MAKE A DIFFERENCE" text "THAT MAKE A DIFFERENCE" text is displaying | Low
| Chorme | AI-Enabled Products, Solutions & Services - Font size is displaying high as compared with mocup | Low
| IE | In IE all the screen we have issues with images - Images are not displaying properly and misalignments in icons and content not displaying for few popups | High
| Chorme | We develop solutions that enable you to realize the true potential of AI text - Products text is missing like text should be products and solutions | Medium
| Chorme | Radio buttons should not displaying properly (Blur on icon background) - Under AI-Enabled Products, Solutions & Services | Low
| Chorme | Advanced Analytics, Engineering & Visualization practices - Instead of engineering it should be "Data Engineering" - Data text missing | Medium
| Chorme | End-to-end Solutions, 24/7 Support, Technology Agnostic, Smart Innovations icons image size should be decreased and for background image are not displaying completely | Low
| Chorme | Industries heading and all industry names and read more link missing in home screen | High
| Chorme | Industries images and icon image size should be decreased - displaying high compare to mocups | Low
| Chorme | Our services section - AI/ML services should be displaying instead of AI/ML | Medium
| Chorme | Learn More Link in Our services section - Arrow missing for Learn More and For all Leran More links should be different colors as per mocups | Low
| Chorme | Company names not in line as per design in home screen | Low
| Chorme | As per design "Improved campaign effectiveness" text missing in Propensity modelling popup under case studies | Medium
| Chorme | Learn More Link in Case studies section - For all Leran More links should be different in colors as per mocups | Low
| Chorme | For the last popup Instead of "RECOMMENDATION SYSTEM" should be display "PREVENTIVE MAINTENANCE" under case studies also description also be change as per design | High
| Chorme | Careers link not working when click on careers control - Lets grow together section | High
| Chorme | Social links not working when we click on social icons | High
| Chorme | Careers link not working under References section in footer | High
About Us
| Chorme | Innovation Catalyst text is displaying instead of "Your Innovation Catalyst" | Medium
| Chorme | Case studies link background color is displaying but mockup it is not showing - Your Innovation Catalyst popup | Low
| Chorme | Case studies link should have underlined - Your Innovation Catalyst popup | Low
| Chorme | Your Innovation Catalyst popup size should display as high - it should be decreased | Low
| Chorme | Your Innovation Catalyst popup background image is not displayed completely as per design | Medium
| Chorme | Vision Text should right aligned as per design | Low
| Chorme | All the content size in about us screen should high compare to designs | Low
| Chorme | View Location link is not working in our locations section | High
| Chorme | View location Link in our Location section - For all View location links should be different in colors as per mocups | Low
| Chorme | Careers link not working when click on careers control - Lets grow together section | High
Contact Us | Chorme | Contact Us image is taking time to load | High
| Chorme | First Name and Last Name text should not displaying as per design - In desin Name text with fields and the below text fields First and Last is displaying | Medium
| Chorme | First Name ,Last Name and Enter email within the text boxes should be removed | Low
| Chorme | Email Address heading should be displyed as Email | Low
| Chorme | "sri@com" without . Symbol accepting email address - should display validation message | Medium
| Chorme | Success message should be display after submitting the details in contact us page | Medium
| Chorme | View Location link is not working in our locations screen | High
| Chorme | View location Link in our Location section - For all View location links should be different in colors as per mocups | Low
Case Studies | Chorme | Taking time to load the images (Know issue) | Medium
| Chorme | Header line font size need to be resize | Low
| Chorme | Contact Us Backgroud clolor should be visibe to identify a button. | Medium
| Chorme | Typo error on customers'(expected should be customer's) under Requirement. | Low
| Chorme | Duplication of subject in both "PROPENSITY MODELLING & RECOMMENDATION SYSTEM" and "CUSTOMER PROFILE" | High
| Chorme | Duplication of Header & Subject "PROPENSITY MODELLING & RECOMMENDATION SYSTEM" | High
Services | Chorme | Seeing mismatch from mockup design headline to webpage headline. | Low
| Chorme | Font & Background not as per design provided | Medium
| Chorme | Contact Us Backgroud clolor not as per design | Medium